## product backlog
product backlog Id | priority | user story Id | user story name | scrum team assigned | Risk | complexity | type | completeness creteria | comments
1 | High | US001 | As a user, I want to log in to my account | Abhishek Kumar | Medium | Low | functional | 3 days
2 | High | US002 | As a user, I want to search for movies | Abhishek Kumar | Low | Medium | functional | 2 days
3 | High | US003 | As a user, I want to view movie details | Abhishek Kumar | Low | Low | functional | 1 day
4 | Medium | US004 | As a user, I want to select seats | Abhishek Kumar | High | High | functional | 5 days
5 | Medium | US005 | As a user, I want to add concessions | Abhishek Kumar | Low | Medium | functional | 2 days
6 | Low | US006 | As a user, I want to review my booking | Abhishek Kumar | Medium | Low | functional | 3 days
7 | High | US007 | As a user, I want to make a payment | Abhishek Kumar | High | High | functional | 4 days
8 | Medium | US008 | As a user, I want to receive a booking confirmation | Abhishek Kumar | Medium | Medium | functional | 2 days
9 | Low | US009 | As a user, I want to view my booking history | Abhishek Kumar | Low | Low | functional | 1 day
Duration Of Project
2months

## sprint backog 1
ProductBacklog id | UserStoryID | User Story Step number | Task Description | Assigned To | Assigned Date | Estimate time | Status | Actual Time
1 | US001 | 1 | Design login page UI with input fields for username and password | Raghul | 2024-02-20 | 12 hr | completed | 8 hr
|  | 2 | Implement frontend for login page with form validation | Akula Sheshu Varma | 2024-02-21 | 13 hr | completed | 9 hr
|  | 3 | Develop backend logic for user authentication | Raghul | 2024-02-22 | 14 hr | completed | 10 hr
|  | 4 | Integrate frontend and backend for complete login functionality | Akula Sheshu Varma | 2024-02-23 | 15 hr | completed | 11 hr
|  | 5 | Design registration page UI with input fields for username, email, password, and confirm password | Abhishek | 2024-02-24 | 16 hr | completed | 9 hr
|  | 6 | Implement frontend for registration page with form validation | Abhishek | 2024-02-25 | 17 hr | completed | 10 hr
|  | 7 | Implement backend for user authentication | Akula Sheshu Varma | 2024-02-22 | 14 hr | Pending | 11 hr
2 | US002 | 1 | Design movie search interface UI with search bar and filters | ankit keshri | 2024-02-20 | 15 hr | completed | 12 hr
|  | 2 | Implement frontend for movie search with dynamic search results | ankit keshri | 2024-02-21 | 16 hr | completed | 13 hr
|  | 3 | Develop backend logic for fetching and filtering movie data | ankit keshri | 2024-02-22 | 17 hr | completed | 14 hr
|  | 4 | Integrate frontend and backend for complete movie search | ankit keshri | 2024-02-20 | 16 hr | pending | 13 hr
3 | US003 | 1 | Design movie details page UI with information sections | jitendriya jena | 2024-02-20 | 18 hr | completed | 16 hr
|  | 2 | Implement frontend for movie details page with dynamic data | jitendriya jena | 2024-02-21 | 19 hr | completed | 17 hr
|  | 3 | Develop backend logic for fetching and displaying movie data | jitendriya jena | 2024-02-22 | 20 hr | completed | 18 hr
|  | 4 | Integrate frontend and backend for complete movie details | Abhishek Kumar | 2024-02-20 | 19 hr | completed | 17 hr
4 | US004 | 1 | Design seat selection UI with interactive seating map | Akula Sheshu Varma | 2024-02-20 | 21 hr | completed | 19 hr
|  | 2 | Implement frontend for seat selection with seat availability status | ankit keshri | 2024-02-20 | 22 hr | completed | 20 hr
|  | 3 | Develop backend logic for seat availability and reservation | Raghul | 2024-02-20 | 23 hr | completed | 21 hr
|  | 4 | Integrate frontend and backend for complete seat selection | Raghul | 2024-02-21 | 24 hr | completed | 22 hr

## sprint backlog 2
ProductBacklog id | UserStoryID | User Story Step number | Task Description | Assigned To | Assigned Date | Estimate time | status | Actual Time
1 | US005 | 1 | Design concessions interface (Gift Cards, Snacks and Beverages) | jitendriya jena | 2024-02-20 | 12 hr | completed | 8 hr
|  | 2 | Implement concessions functionality | Siva mani raja | 2024-02-21 | 13 hr | completed | 9 hr
2 | US006 | 1 | Create booking review UI | ankit keshri | 2024-02-20 | 15 hr | completed | 12 hr
|  | 2 | Develop backend for booking review | jitendriya jena | 2024-02-20 | 16 hr | pending | 13 hr
3 | US007 | 1 | Design payment interface | Siva mani raja | 2024-02-20 | 18 hr | completed | 16 hr
|  | 2 | Implement payment gateway integration | ankit keshri | 2024-02-20 | 19 hr | completed | 17 hr
4 | US008 | 1 | Create booking confirmation UI | Akula Sheshu Varma | 2024-02-20 | 21 hr | completed | 19 hr
|  | 2 | Integrate booking confirmation with backend | Siva mani raja | 2024-02-20 | 22 hr | completed | 20 hr
5 | US009 | 1 | Design booking history interface | jitendriya jena | 2024-02-22 | 24 hr | completed | 22 hr
|  | 2 | Implement backend for booking history | Siva mani raja | 2024-02-23 | 25 hr | completed | 23 hr